## Sheet1
Cottonwood Overview FHAP |  |  |  | Original Budget |  | *Spent to Date (20- 25% complete) |  | Forecast for Completion (75% remaining) |  | Total Budgeted for | Total Projected
FEES | Unit | office cost/unit | field cost/unit | units | cost | units | cost | units | cost
Fish Habitat Specialist | Day | 450 | 500 | 3 | 1350 |  |  | 3 | 1350 | 1350 | 1350
Fisheries Biologist | Day | 400 | 450 | 21 | 8400 | 21 | 8400 | 63 | 25200 | 8400 | 33600
Fisheries Technician (2 techs) | Day | 300 | 330 | 12 | 3600 | 17 | 5100 | 51 | 15300 | 3600 | 20400
GIS Specialist | Day | 450
GIS Technician | Day | 325
Total Fees |  |  |  |  | 13350 |  | 13500 |  | 41850 | 13350 | 55350
Disbursements
Air Flights | est | 400 |  | 1 | 400 |  |  |  | 400 | 400 | 400
Preparation of GIS map | est | 40
Mileage | km | 0.37
Off Road Truck Rental | day | 32
Helicopter | hour | 800 |  | 4 | 3200 |  |  |  | 3200 | 3200 | 3200
Maps (4) | est | 50 |  | 4 | 200 |  |  |  | 200 | 200 | 200
Phone/Fax/Courier | est | 150 |  | 1 | 150 |  |  |  | 150 | 150 | 150
Field GPS Rental | month | 100
Electroshocker Rental | month | 500
Field Kit Rental | week | 150
Misc. Reports, Supplies,etc. | est | 100 |  | 1 | 100 |  |  |  | 100 | 100 | 100
Photocopying/report product | est | 200 |  | 1 | 200 |  |  |  | 200 | 200 | 200
Accommodation (3 people) | Day | 70
Meals | Day | 36 |  | 1 | 36 |  |  |  | 36 | 36 | 36
Photographs | est | 100
Misc. | est | 100 |  | 1 | 100 |  |  |  | 100 | 100 | 100
TOTAL EXPENSES |  |  |  |  | 4386 |  | 0 |  | 4386 | 4386 | 4386
TOTAL |  |  |  |  | 17736 |  | 13500 |  | 46236 | 17736 | 59736
* based on the # of sub-basins in our proposal and the number of km's of stream length completed versus what we said we would do.