## Sheet1
Upper Bowron Overview FHAP |  |  |  | Original Budget |  | *Spent to Date (43- 54% complete) |  | Forecast for Completion (approx 50% remaining) |  | Total Budgeted for | Total Projected
FEES | Unit | office cost/unit | field cost/unit | units | cost | units | cost | units | cost
Fish Habitat Specialist | Day | 590 | 590 | 3 | 1770 |  |  | 3 | 1770 | 1770 | 1770
Fisheries Biologist | Day | 400 | 450 | 20 | 8000 | 12.3 | 4920 | 13 | 5200 | 8000 | 10120
Fisheries Technician (2 techs) | Day | 300 | 330 | 10 | 3000 | 14.7 | 4410 | 15 | 4500 | 3000 | 8910
GIS Specialist | Day | 450
GIS Technician | Day | 325
Total Fees |  |  |  |  | 12770 |  | 9330 |  | 11470 | 12770 | 20800
Disbursements
Air Flights | est | 400 |  | 1 | 400 |  |  |  | 400 | 400 | 400
Preparation of GIS map | est | 40
Mileage | km | 0.37
Off Road Truck Rental | day | 32
Helicopter | hour | 800 |  | 4 | 3200 |  |  |  | 3200 | 3200 | 3200
Maps (4) | est | 50 |  | 4 | 200 |  |  |  | 200 | 200 | 200
Phone/Fax/Courier | est | 150 |  | 1 | 150 |  |  |  | 150 | 150 | 150
Field GPS Rental | month | 100
Electroshocker Rental | month | 500
Field Kit Rental | week | 150
Misc. Reports, Supplies,etc. | est | 100 |  | 1 | 100 |  |  |  | 100 | 100 | 100
Photocopying/report product | est | 200 |  | 1 | 200 |  |  |  | 200 | 200 | 200
Accommodation (3 people) | Day | 70
Meals | Day | 36 |  | 1 | 36 |  |  |  | 36 | 36 | 36
Photographs | est | 100
Misc. | est | 100 |  | 1 | 100 |  |  |  | 100 | 100 | 100
TOTAL EXPENSES |  |  |  |  | 4386 |  | 0 |  | 4386 | 4386 | 4386
TOTAL |  |  |  |  | 17156 |  | 9330 |  | 15856 | 17156 | 25186
* based on the # of sub-basins in our proposal and the number of km's of stream length completed versus what we said we would do.