J.M.Ryder and Associates, Terrain Analysis Inc.

P.O.Box 45005, Dunbar P.O., Vancouver, B.C.  Canada,  V6S 2M8        Ph 604-736-4211  Fax 604-736-5101

Mr. Don Howes								May 10th, 1996

Program Manager -- Land Inventory and Information Analyst

Land Use Coordination Office

1--836 Yates Centre, Victoria, British Columbia, V8V 1X4

Dear Don:

Here is a proposal for hazard mapping for the Mid-Coast Region, as discussed with you at our meeting April 25th.

Our time and cost estimates for the pilot project are deliberately generous since it is hard to estimate the time required for developing the methodology. We prefer to have time available to think carefully about the integration and analysis of the data using the GIS facilities that you are providing, and to determine the best way to output the final maps. If we have over-budgeted for this part of the project, the unused funds will be applied to the second half of the project. Although the second half of the project involves mapping a larger area, methods will have been standardized, and so it will require much less input from us.

We have selected the southern half of 92M and southwestern quarter of 92N for the pilot project because TRIM maps are available for this area. We are planning to use the TRIM maps for estimates of slope steepness (slope maps), and so completion of the mapping to the standards that we will set in the pilot project will require that TRIM mapping be available for the entire map area.

Note that although the Project Budget shows all times in terms of "DM/JMR days", technical work and routine air photo interpretation will be carried out by JMRATA staff under our supervision, at per diems of $270-$320. Thus more days of work time are available than indicated in the budget.

If you have any questions or require further information or discussion, give us a call. We look forward to working with you and your staff on this project. Please phone either of us to discuss any of the contents of this proposal. Resumes of everyone who will work on the project are available upon request.

We thank you for inviting us to submit this proposal.

Yours sincerely,

June M. Ryder, P.Geo.				Denny Maynard, P.Geo.

per							per

J.M.Ryder and Associates, 				Denny Maynard and Associates. Ltd.

Terrain Analysis Inc.

J.M.Ryder and Associates, Terrain Analysis Inc.

P.O.Box 45005, Dunbar P.O., Vancouver, B.C.  Canada,  V6S 2M8        Ph 604-736-4211  Fax 604-736-5101

May 9th, 1996

Proposal For Terrain Hazard Mapping, British Columbia Mid-Coast Region

Objectives:

To prepare 1:250 000 scale hazard maps for use in broad forest zoning and regional planning. The maps will show: slope hazards (landslide initiation zones, runout zones, potentially unstable slopes); areas affected by snow avalanches; areas of potential flooding and other fluvial hazards, potential initiation sites for glacier-burst and moraine-burst floods; areas of hazardous (e.g., sensitive) soils.

Methods

(A) Pilot Project: To develop methods for preparation of hazard maps.

Sample area: southern half of 92M and southwestern quarter of 92N.

Tasks:

(1) Review data that already exist in GIS (Don Howes office) and become familiar with GIS capabilities. (With help from GIS staff, review TRIM maps, bedrock geology mapping, biogeoclimatic zones maps, other climate maps. Check quality of maps; generate 1:100 000 base maps; generalize bedrock maps; determine classes for preparation of slope maps; prepare preliminary slope+bedrock maps.  		(6 days DM/JMR)

(2) Compile and review existing non-GIS information: terrain maps and surficial geology maps of various scales and dates; geomorphological reports; bedrock geology reports; engineering studies; other relevant literature. Purchase air photos (1:60 000 TRIM photos).

(4 days DM/JMR)

(3) Develop methodology (and legend) for air photo interpretation; air photo interpretation by (DM, JMR and JMRATA terrain mappers); transfer interpreted data to TRIM base by hand. Do reliability checks: e.g., hand vs. photogrammetric transfer; 1:60 000 mapping results vs. existing terrain stability mapping; 1:60 000 mapping results vs. mapping on larger scale and more recent photographs.			(18 days DM/JMR)

(4) Compile data from above tasks and work with GIS staff to develop interpretations and presentation style for hazard maps.				(10 days DM/JMR)

(5) Prepare report outlining methodology recommended for subsequent map production for remainder of region.							(8 days DM/JMR)

(B) To Prepare Hazard Maps for the Remainder of the Mid-Coast Region

(6) Tasks (1) and (2) above.						(4 days DM/JMR)

(7) Air photo interpretation; transfer interpreted data to TRIM base maps.

(40 days DM/JMR)

(8) Compile data from (6) and (7), and work with GIS staff to carry out interpretations for hazard maps.								(8 days DM/JMR)

(9) Prepare regional report.						( 8 days DM/JMR)

Estimated Project Completion Dates

Part (A): September 30, 1996

Part (B): December 31, 1996

Project Budget

Summary

A proposed budget for the entire project is outlined on the following page. Total cost is $80 000., of which $33 600. ($29 900. for fees, $3700. for expenses) is for the Pilot Project, and $46 400. ($39 000. fees, $7400. expenses) is to complete mapping of the entire area. The proportionally higher initial cost generously provides for sufficient time to develop a thorough and reliable methodology. Any savings which can be made in the Pilot Project will accrue to the remainder of the project.

(A) Pilot Project

Task 	(1) 6 days DM/JMR* @ $650.			  $3900.00

(2) 4 days DM/JMR @ $650.			  $2600.00

(3) 18 days DM/JMR @ $650.			$11 700.00

(4) 10 days DM/JMR @ $650.			  $6500.00

(5) 8 days DM/JMR @ $650.			  $5200.00

Total professional time:								$29 900.00

Expenses:

air photos ($1250.00) and other project

materials:						$1700.00

office expenses, including phone, courier,

supplies, photocopying				  $500.00

travel: 6 round trips to Victoria, or other

destination re. data collection,

incl. accom. for 2-day trips 			$1000.00

contingency						  $500.00

Total 											  $3700.00

Total Pilot Project									$33 600.00

(B) To Complete Project

Task 	(6) 4 days DM/JMR @ $650.			  $2600.00

(7) 40 days DM/JMR @ $650.			$26 000.00

(8) 8 days DM/JMR @ $650.			  $5200.00

(9) 8 days DM/JMR @ $650.			  $5200.00

Total											$39 000.00

Expenses:

air photos ($5000.) and other project materials:	$5500.00

office expenses, including phone, courier,

supplies, photocopying				  $600.00

travel: 4 round trips to Victoria, or other,

including accom. for 2-day trips 			  $800.00

contingency						  $500.00

Total 											$7400.00

Total to complete project								$46 400.00

Total (A) and (B)									$80 000.00

* Times are estimated in days for DM and JMR, but technical work and routine air photo interpretation will be completed by JMRATA staff (terrain mappers) under the supervision of DM or JMR, giving about twice as much work time for equivalent cost.